## Dashboard
WOHLIG PROJECT DASHBOARD
Total Employees 31 |  | Total Projects 10 | Locations 6 | Updated 01-June-2026
Location | Count
Office | 21
Marol | 2
Delhi | 3
WFH | 1
Bangalore branch | 2
Airoli | 1

## Active
WOHLIG DEVELOPER PROJECT REPORT
No. | Active Employee | DOJ | Current Role | Current Project | Current Work location | Project Start | Project End | Reporting To
1 | Pratik Sawant | 2022-09-05 | Software Developer | Vaultify | Office | 2026-02-09 | 2026-11-03 | Jagruti Shah
2 | Osama Patel | 2023-04-26 | Software Developer | JM Finance | Marol | 2026-02-18 |  | Jagruti Shah
3 | Swaraj Baswad | 2023-06-01 | Software Developer | JM Finance | Marol | 2025-12-15 |  | Jagruti Shah
4 | Samay Gada | 2023-07-01 | Tech Lead |  | Bangalore branch |  |  | Chintan Shah
5 | Bilal Sani | 2023-07-01 | Tech Lead | Jindal Steel | Delhi | 2026-05-25 | 2026-09-25 | Chintan Shah
6 | Ramesh Lodh | 2024-01-17 | DevOps | TUI | WFH | 2026-02-09 | 2026-06-24 | Kailash Lakampelli
7 | Jainam Nisar | 2024-09-01 | Software Developer | Jindal Steel | Delhi | 2026-05-25 | 2026-09-25 | Bilal Saini
8 | Dhruv Gansinghani | 2024-09-01 | Gen AI Developer | Mahindra CFO | Office | 2026-05-25 | 2026-08-25 | Bilal Saini
9 | Naveed Shaikh | 2024-09-02 | Devops | Jindal Steel | Delhi | 2026-05-25 | 2026-09-25 | Bilal Saini
10 | Jagruti Shah |  | Product Manager | Vaultify | Office | 2026-02-09 | 2026-11-03 | Chintan Shah
11 | Mustafa Mohammed | 2025-05-01 | Software Developer | Apollo Hispital | Office | 2026-04-20 | 2026-06-02 | Samay Gada
|  |  |  | Jindal Steel | Office | 2026-05-25 | 2026-09-25 | Bilal Saini
12 | Arham Sangoi | 2025-05-01 | Gen AI Developer | Mahindra CFO | Office | 2026-05-25 | 2026-08-25 | Bilal Saini
13 | Hanishka Jain | 2025-11-01 | Video Editor | Pocket Studio | Office | 2026-05-11 |  | Chintan Shah
14 | Agam Shah | 2025-11-13 | Gen AI Developer | Vaultify | Office | 2026-02-09 | 2026-11-03 | Jagruti Shah
|  |  |  | Apollo Hispital |  | 2026-04-20 | 2026-06-02 | Samay Gada
15 | Siddesh Kale | 2026-02-01 | Software Developer | No Task | Office |  |  | Dhruv Gansinghani
16 | Nishant Patil | 2026-02-01 | Software Developer | No Task | Office |  |  | Dhruv Gansinghani
17 | Rajvee Gala |  | Data Analysist | IKS SRE | Airoli |  |  | Chintan Shah
18 | Shubham Jain | 2026-04-08 | Gen AI - Intern | Weekly automation task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
19 | Shubham Satpute | 2026-04-09 | Gen AI - Intern | Weekly automation task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
20 | Chintan Limbad | 2026-04-20 | Data Engineer - Fresher | No Task | Office |  |  | Rajvee Gala
21 | Praveen Kumar | 2026-04-22 | Gen AI - Fresher | No Task | Bangalore branch |  |  | Samay Gada
22 | Aryan Gupta | 2026-05-04 | Gen AI - Intern | GenAI Learning Task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
23 | Dhruv Solanki | 2026-05-04 | Gen AI - Intern | GenAI Learning Task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
24 | Nishita Patel | 2026-05-04 | Gen AI - Intern | GenAI Learning Task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
25 | Dhruv Bharwada | 2026-05-04 | Gen AI - Intern | E-Mail automation | Office | 2026-06-01 | 2026-06-16 | Chintan Shah
26 | Harsh Mishra | 2026-05-04 | Gen AI - Intern | E-Mail automation | Office | 2026-06-01 | 2026-06-16 | Chintan Shah
27 | Akshay Ahuja | 2026-05-04 | Gen AI - Intern | Vaultify | Office | 2026-06-01 | 2026-11-03 | Jagruti Shah
28 | Sakshi Patil | 2026-05-04 | Gen AI - Intern | Vaultify | Office | 2026-06-01 | 2026-11-03 | Jagruti Shah
29 | Jigar Rambhiya | 2026-05-15 | Machine learning - Intern | No Task | Office |  |  | Rajvee Gala
30 | Parth Gala | 2026-06-01 | Sr. Backend Developer | GenAI Learning Task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav
31 | Krishank Daga | 2026-06-01 | Gen AI - Intern | GenAI Learning Task | Office | 2026-06-01 | 2026-06-16 | Ankit Shrivastav

## Exit
No. | Employee Name | LWD | Replaced By | Projects

## Project
Sr No. | Project Name | Client Name | Owner Name | Owner Email | Project Team | Start Date | End Date | Status
1 | Apollo Hospital | Apollo Hospital | Mustafa Mohammed | mustafa.mohammed@wohlig.com | Mustafa Mohammed Agam Shah Chintan Limbad | 2026-04-20 | 2026-05-31 | Done
2 | Mahindra CFO | Mahindra | Jainam Nisar | jainam.nisar@wohlig.com | Dhruv Gansinghani Arham Sangoi | 2026-05-26 | 2026-09-25 | In Progress

## Retainers
Project Name | Client Name | Owner Name | Project Team | Project Start Date | Monthly Cost | Renewal Date | Status
Vaultify | VATSAL DESAI | Jagruti Shah | Pratik Sawant Sakshi Patil Akshay Ahuja Agam Shah Jagruti Shah | 2026-02-09 |  |  | In Progress
Jindal Steel | Jindal Steel | Chintan Shah | Bilal Sani Jainam Nisar Naveed Shaikh Mustafa Mohammed | 2026-05-26 |  |  | In Progress
IKS SRE | IKS | Chintan Shah | Rajvee Gala |  |  |  | In Progress
JM Finance | JM Finance | Jagruti Shah | Osama Patel Swaraj Baswad | 2026-02-18 |  |  | In Progress
TUI | TUI | Kailash | Ramesh Lodh | 2026-02-09 |  |  | In Progress

## Internal
Project Name | Client Name | Owner Name | Owner Email | Project Team | Start Date | End Date | Status
Pocket Studio | Wohlig | Chintan Shah | chintan@wohlig.com | Aiman Ansari Wajid Jamadar | 2025-07-14 | 2026-05-20 | Closed
GenAI Learning Task | Wohlig | Ankit Shrivastav | ankit.shrivastav@wohlig.com | Aryan Gupta Dhruv Solanki Krishank Daga Nishita Patel Parth Gala | 2026-06-01 | 2026-06-16 | Active
Weekly Automation Task | Wohlig | Ankit Shrivastav | ankit.shrivastav@wohlig.com | Shubham Jain Shubham Satpute | 2026-06-01 | 2026-06-16 | Active
E-mail Automation | Wohlig | Chintan Shah | chintan@wohlig.com | Harsh Mishra Dhruv Bharwada | 2026-06-01 | 2026-06-16 | Active